## Sheet1
Task | Start Date | Days to complete
1 Planning & Design Phase | 2023-05-12 | 10
1.1 Project Planning & Features Selection | 2023-05-12 | 4
1.2 Create a Roadmap | 2023-05-16 | 3
1.3 Project Proposal | 2023-05-19 | 3
2 Development Phase | 2023-06-02 | 42
2.1 Database Connection & Design | 2023-06-02 | 3
2.2 Login Page Design & Implementation | 2023-06-05 | 15
2.3 Home Page UI Design | 2023-06-05 | 15
2.4 Backend Implementation of Product Interface | 2023-06-20 | 12
2.5 Backend Implementation of Customer Interface | 2023-06-20 | 12
2.6 Backend Implementation of Invoice | 2023-07-02 | 6
2.7 Backend Implementation of Logout & Close App | 2023-07-08 | 6
3 Testing & Quality Assurance | 2023-07-19 | 16
3.1 Debugging | 2023-07-19 | 10
3.2 Cross Device Testing | 2023-07-29 | 6
4 Launch | 2023-08-06 | 16
4.1 Report Writing & Presentation | 2023-08-06 | 11
4.2 Final launch | 2023-08-06 | 16